# Fiscal Patriots

AGA Datathon 2026 Team Collaboration Hub

# Project Overview

Competition: AGA (Association of Government Accountants) Datathon 2026

Team Name: Fiscal Patriots

Institution: George Mason University, Costello College of Business

Primary Contact: Jennifer Garrett, PMP (jgarrett@agacgfm.org)

Team Sync meetings: Friday’s at 10am.

# Selected Use Case

Use Case 1: Social Impact of Government Programs

## Challenge

Analyze the relationship between government spending on specific programs (e.g., Social Security, Medicaid) and social indicators like poverty rates, unemployment, or access to healthcare.

## Goal/Objective

Identify which programs deliver the highest return on investment in terms of societal benefits.

# Key Dates & Milestones

| Date | Milestone |
| --- | --- |
| Dec 1, 2025 | Application closes |
| Dec 2, 2025 | Kickoff Zoom Call (Noon ET) |
| Jan 18, 2026 | PROJECT SUBMISSION DEADLINE |
| Jan 20-23, 2026 | Teams present projects via Zoom |
| Jan 26, 2026 | Top 3 teams announced |
| Feb 18, 2026 | Finals at AGA NLT (Washington, D.C.) |

# Team Contact Information

| Team Member | Email |
| --- | --- |
| Khaled Alkurd | kalkurd@gmu.edu |
| Pranavi Doodala | ldoodala@gmu.edu |
| Nikita Chandrasing | Nchandr3@gmu.edu |
| Mariam Debas | mdebas@gmu.edu |
| Andy Yaro | yyaro@gmu.edu |

## Team Skills Matrix

| Team Member | Degree | Core Strengths & Skills |
| --- | --- | --- |
| Khaled | MS Accounting Analytics & Forensic Accounting | Financial analysis, forensic accounting, operations management |
| Pranavi | BS Business Analytics | AI/data analysis (HUD), Python, Selenium, data scraping, narrative building |
| Nikita | BS MIS & Business Analytics | SQL, Python, R, Tableau, APIs, OpenAI API, data visualization |
| Mariam | BS Accounting & MIS | Data visualization, Tableau, Excel, financial reporting, accounting analysis |
| Andy | BS Cybersecurity | GitHub, API integration, network security, technical infrastructure |

# Key Data Sources

Official government data sources for Use Case 1 (Social Impact of Government Programs):

| Source | Description & Use Case |
| --- | --- |
| USAspending.gov | Federal spending by agency, program, and recipient. Track Social Security, Medicaid, SNAP expenditures. |
| FiscalData.Treasury.gov | Treasury financial data, debt, and revenue. Understand the overall fiscal context of program spending. |
| Census.gov | Poverty rates, income data, healthcare coverage, and demographic trends. Key social outcome indicators. |
| BLS.gov | Unemployment rates, labor force participation. Critical for measuring employment program outcomes. |
| Data.gov | Open government datasets across all agencies. Supplementary data for cross-referencing. |
| CMS.gov | Medicare and Medicaid data. Essential for healthcare access and program impact analysis. |

# Recommended Starting Steps

Follow these steps to hit the ground running as a team:

## Week 1: Foundation (Dec 2-8)

☒ Attend Kickoff Zoom Call (Dec 2, Noon ET) and take notes on requirements

☐ Set up GitHub repository (Andy) and invite all team members

☒ Create OneDrive folder structure (Khaled) see separate Folder Structure document

☒ Schedule weekly team sync meetings (Khaled) and establish communication channels

## Week 2: Research & Data Collection (Dec 9-15)

☐ Explore data sources (Pranavi & Nikita) and identify key datasets for analysis

☐ Document data dictionaries (Nikita & Andy) and note variable definitions

☐ Set up API connections (Andy & Nikita) for automated data pulls where available

☐ Draft initial analysis plan (Khaled & Mariam) with hypotheses to test

## Week 3-4: Analysis & Visualization (By Jan 5)

☐ Run statistical analyses (Pranavi, Nikita, Khaled) to identify program ROI patterns

☐ Create initial visualizations (Mariam, Nikita, Khaled) to support key findings

☐ Develop narrative thread (Pranavi) connecting spending to social outcomes

☐ Maintain version control (Andy) and document all code changes

☐ Team Rehearsal prior to draft submission

☐ Submit Draft to Professor Clement Chen for feedback

## Week 5-6: Deliverables (Jan 6-18)

☐ Finalize visualizations and ensure they clearly communicate insights

☐ Draft final report (Khaled & Mariam) with executive summary, methodology, findings

☐ Create presentation slides for Zoom presentation (Jan 20-23)

☐ Conduct team rehearsals and refine delivery

☐ Submit by Jan 18 deadline (do not wait until last minute!)

## Role-Based Recommendations

| Team Member | Suggested Focus Areas |
| --- | --- |
| Khaled | Team coordination, financial analysis framework, final report oversight, presentation delivery |
| Pranavi | Lead data analysis (Python), narrative development, data scraping, storytelling framework |
| Nikita | SQL data prep, R analysis, API integration support, Tableau dashboards, AI-assisted insights |
| Mariam | Visualization design (Tableau/Excel), chart creation, financial reporting alignment, visual QA |
| Andy | GitHub repo management, API data pipelines, technical infrastructure, code documentation |

Let's bring home the win, Fiscal Patriots!